## Header
DHWANI RIS - PROJECT PLAN
Project Name | PRIME Rural Fellowship Platform - Web CRM
Project ID | PREF-CRM-WEB
Client | MBMA (Meghalaya Basin Management Agency)
Delivery Team | Dhwani Rural Information Services
Project Start Date | 2025-09-01
Planned Go-Live Date | 2026-08-03
Plan Version | v6.0
Plan Date | 2026-05-26
Plan Author | Samarth Paul (PM)
UAT-1 Date | 2026-05-29 | User Mgmt + Masters + EP Profile + Product Profile + 27 Frameworks + Fellow Activity Logger
UAT-2 Date (proposed) | 2026-06-12 | Research Notes + Village Survey + Landscape Dashboard + Milestone Tracker polish
UAT-3 Date | TBD | Intervention Dashboard + KPI + Apoorva AI + Claude Chatbot - pending requirement finalisation

## Project Plan
S.No | WBS | Activity | Duration (Days) | Resources | Dependency | Owner | Success Criteria | Current Status | UAT Batch | Start Date | End Date | Actual Start Date | Actual End Date
1 | 1 | System Foundation | 14 | DevOps / Tech Lead |  | Prakash | Staging environment live; auth + role infra ready for app development | Completed | Pre-UAT | 2025-09-01 | 2025-09-14 | 2025-09-01 | 2025-09-14
2 | 1.1 | Frappe v16 staging environment setup | 3 | DevOps |  | Prakash | stgprime-rural.dhwaniris.in live with HTTPS | Completed | Pre-UAT | 2025-09-01 | 2025-09-03 | 2025-09-01 | 2025-09-03
3 | 1.2 | GitHub repo + CI/CD hooks (dhwani-ris/frappe_prime_rural) | 2 | Backend Dev | 1.1 | Navneet | Repo with pre-commit hooks + branch protections | Completed | Pre-UAT | 2025-09-04 | 2025-09-05 | 2025-09-04 | 2025-09-05
4 | 1.3 | API token authentication setup + testing | 1 | Backend Dev | 1.1 | Navneet | Admin API calls succeed with token header | Completed | Pre-UAT | 2025-09-06 | 2025-09-06 | 2025-09-06 | 2025-09-06
5 | 1.4 | MSG91 OTP integration (mobile auth backend) | 3 | Backend Dev | 1.1 | Navneet | OTP send + verify endpoints live for Flutter app | Completed | Pre-UAT | 2025-09-07 | 2025-09-09 | 2025-09-07 | 2025-09-09
6 | 1.5 | Google SSO configuration (Gmail-based users) | 2 | DevOps | 1.1 | Prakash | Gmail users land in Frappe via OAuth without password | Not Started | UAT-1 | 2026-05-26 | 2026-05-28
7 | 1.6 | Welcome email custom template (set-password link) | 1 | Backend Dev | 1.5 | Navneet | New users receive role-aware welcome email with set-password link | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
8 | 2 | User Management | 10 | Developer / Tech Lead | 1 | Navneet | Core Team IT can add users, assign roles + blocks; users can log in | In Progress | UAT-1 | 2025-10-10 | 2026-05-28 | 2025-10-10
9 | 2.1 | Add User form (6 fields: name, email, phone, role, district, block) | 4 | Frontend Dev | 1 | Navneet | Form validates + creates Frappe User + assigns role; BRD PR-XC-001 | In Progress | UAT-1 | 2025-10-10 | 2026-05-28 | 2025-10-10
10 | 2.2 | Role assignment logic (6 roles -> sidebar menu) | 5 | Tech Lead | 2.1 | Bhushan | Each role lands on its own workspace; sidebar items hidden per role | In Progress | UAT-1 | 2025-10-12 | 2026-05-28 | 2025-10-12
11 | 2.3 | Login flow: email + password | 2 | Backend Dev | 1 | Navneet | Standard Frappe login active for non-Gmail users | Completed | UAT-1 | 2025-10-15 | 2025-10-16 | 2025-10-15 | 2025-10-16
12 | 2.4 | Login flow: Google SSO for Gmail users | 2 | DevOps | 1.5 | Prakash | Gmail users log in via Google button | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
13 | 2.5 | Block assignment for Fessociates -> auto-fill District/Block | 2 | Backend Dev | 2.1 | Navneet | Fessociate sees only their block's EPs; admin can override | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
14 | 2.6 | District Coordinator: view-all edit-none permission set | 2 | Tech Lead | 2.2 | Bhushan | DC can browse all data but Save buttons disabled per role rule | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
15 | 2.7 | Designer role: restricted sidebar + upload-only permissions | 2 | Tech Lead | 2.2 | Bhushan | Designer sees only Logo/Label/Brochure draft upload screens | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
16 | 2.8 | SELCO Executive role: restricted to Infrastructure EE tab | 2 | Tech Lead | 2.2 | Bhushan | SELCO sees only EE pricing entry + solarisation approval flow | Not Started | UAT-1 | 2026-05-27 | 2026-05-28
17 | 3 | Masters | 18 | Developer / Tech Lead | 1 | Navneet | All seed masters loaded + linked across the doctype graph | Completed | UAT-1 | 2025-09-15 | 2025-10-05 | 2025-09-15 | 2025-10-05
18 | 3.1 | District + Block + Village master (Meghalaya hierarchy) | 4 | Backend Dev | 1 | Navneet | All Meghalaya districts/blocks/villages loaded + cascading lookup live | Completed | UAT-1 | 2025-09-15 | 2025-09-18 | 2025-09-15 | 2025-09-18
19 | 3.2 | Sector + Business Basket + Product Type masters | 2 | Backend Dev | 1 | Navneet | Sector picker cascades to Business Basket then Product Type | Completed | UAT-1 | 2025-09-19 | 2025-09-20 | 2025-09-19 | 2025-09-20
20 | 3.3 | Cohort master | 1 | Backend Dev | 1 | Navneet | Cohort picker available on EP Profile | Completed | UAT-1 | 2025-09-21 | 2025-09-21 | 2025-09-21 | 2025-09-21
21 | 3.4 | Packaging master (12 types: Glass Jar ... Other) | 1 | Backend Dev | 1 | Navneet | All 12 packaging types selectable in Packaging framework | Completed | UAT-1 | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22
22 | 3.5 | Registration master (20 registration types) | 3 | Backend Dev | 1 | Navneet | All 20 registration types selectable in Registration framework | Completed | UAT-1 | 2025-09-23 | 2025-09-25 | 2025-09-23 | 2025-09-25
23 | 3.6 | Test Type master (14 test types) | 1 | Backend Dev | 1 | Navneet | Test type picker live in Product Testing framework | Completed | UAT-1 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26
24 | 3.7 | Lab master (12 labs) | 1 | Backend Dev | 1 | Navneet | Lab picker live in Product Testing framework | Completed | UAT-1 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-27
25 | 3.8 | Standardisation Type master (13 types) | 1 | Backend Dev | 1 | Navneet | All 13 SOP types selectable in Standardization framework | Completed | UAT-1 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28
26 | 3.9 | Scheme master (17 govt schemes) | 2 | Backend Dev | 1 | Navneet | All 17 schemes selectable in Funding framework | Completed | UAT-1 | 2025-09-29 | 2025-09-30 | 2025-09-29 | 2025-09-30
27 | 3.10 | Role setup: 6 roles with permission rules | 5 | Tech Lead | 1 | Bhushan | Core IT, Core Prog, Fessociate, Designer, SELCO, DC roles created with default permissions | Completed | UAT-1 | 2025-10-01 | 2025-10-05 | 2025-10-01 | 2025-10-05
28 | 4 | Entrepreneur Profile | 31 | Developer | 3 | Navneet | Fessociates can create + maintain entrepreneur records end-to-end | In Progress | UAT-1 | 2025-10-06 | 2026-05-28 | 2025-10-06
29 | 4.1 | EP doctype backend (all fields + naming rule) | 5 | Backend Dev | 3 | Navneet | EP-{name}-##### naming; all fields validated server-side | Completed | UAT-1 | 2025-10-06 | 2025-10-10 | 2025-10-06 | 2025-10-10
30 | 4.2 | Vue: Profile Dashboard (9 sub-components) | 9 | Frontend Dev | 4.1 | Navneet | Single-page entrepreneur view with stats + product shelf + DF rollup | Completed | UAT-1 | 2025-10-12 | 2025-10-20 | 2025-10-12 | 2025-10-20
31 | 4.3 | Vue: Selection tab (10 rating fields + Rural E-Champ) | 3 | Frontend Dev | 4.2 | Navneet | Average rating auto-calculates; Rural E-Champ flag works | Completed | UAT-1 | 2025-10-21 | 2025-10-23 | 2025-10-21 | 2025-10-23
32 | 4.4 | Vue: Prioritisation tab | 1 | Frontend Dev | 4.2 | Navneet | Cards reorder on dashboard by priority value | Completed | UAT-1 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24
33 | 4.5 | Vue: Location & Contact + Geolocation pin | 3 | Frontend Dev | 4.2 | Navneet | Map pin saved; reverse-geocode populates district/block | Completed | UAT-1 | 2025-10-25 | 2025-10-27 | 2025-10-25 | 2025-10-27
34 | 4.6 | Vue: Documents tab + photo gallery | 1 | Frontend Dev | 4.2 | Navneet | Documents upload + preview + lightbox gallery | Completed | UAT-1 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28
35 | 4.7 | Vue: Networking & Mentoring tab (inline intro + meeting log) | 7 | Frontend Dev | 4.2 | Navneet | PR feat/networking-mentoring-v2 merged; auto-sync meeting counts to parent | Completed | UAT-1 | 2025-10-29 | 2025-11-05 | 2025-10-29 | 2025-11-05
36 | 4.8 | Vue: Intervention Logs (read-only sync from Activity Logger) | 14 | Frontend Dev | 9 | Navneet | Every Activity Logger entry surfaces on EP timeline read-only | In Progress | UAT-1 | 2025-11-06 | 2026-05-28 | 2025-11-06
37 | 5 | Product Profile | 28 | Developer | 4 | Navneet | All entrepreneur products captured with variants, process flow + production capacity | In Progress | UAT-1 | 2025-11-06 | 2026-05-28 | 2025-11-06
38 | 5.1 | Product doctype backend + child tables | 3 | Backend Dev | 4 | Navneet | Product + variant + process step doctypes deployed | Completed | UAT-1 | 2025-11-06 | 2025-11-08 | 2025-11-06 | 2025-11-08
39 | 5.2 | Vue: Product Details tab (12 fields) | 6 | Frontend Dev | 5.1 | Navneet | Form populates + saves; product type integration live | Completed | UAT-1 | 2025-11-09 | 2025-11-15 | 2025-11-09 | 2025-11-15
40 | 5.3 | Vue: Product Variants tab (SKU auto-gen + volume calc) | 7 | Frontend Dev | 5.1 | Navneet | SKU = VARIANT-SUBVARIANT-WEIGHT-UNIT; volume = LxBxH auto | Completed | UAT-1 | 2025-11-16 | 2025-11-22 | 2025-11-16 | 2025-11-22
41 | 5.4 | Vue: Process Flow tab (drag-drop reorderable steps) | 6 | Frontend Dev | 5.1 | Navneet | Drag-drop reorders + saves; machine + flow master linked | Completed | UAT-1 | 2025-11-23 | 2025-11-28 | 2025-11-23 | 2025-11-28
42 | 5.5 | Vue: Production Capacity tab (agri-conditional + monthly tracker) | 60 | Frontend Dev | 5.3 | Navneet | Available Months x Variants matrix renders + saves per-variant qty | In Progress | UAT-1 | 2025-11-29 | 2026-05-28 | 2025-11-29
43 | 5.6 | Available Months checkbox logic -> tracker generation | 30 | Frontend Dev | 5.5 | Navneet | Selecting months auto-creates corresponding columns in tracker | In Progress | UAT-1 | 2025-12-01 | 2026-05-28 | 2025-12-01
44 | 6 | Diagnostic Frameworks (27) | 130 | Developer | 5 | Navneet | All 27 framework forms deployed; entrepreneurs can be diagnosed end-to-end | In Progress | UAT-1 | 2025-12-01 | 2026-05-28 | 2025-12-01
45 | 6.1 | Manufacturing - Raw Materials | 5 | Frontend Dev | 5 | Navneet | Existing + Required tabs with Cost/Batch calc + Summary | Completed | UAT-1 | 2025-12-01 | 2025-12-05 | 2025-12-01 | 2025-12-05
46 | 6.2 | Manufacturing - Machinery | 5 | Frontend Dev | 5 | Navneet | 22 fields + 7 calcs + depreciation + solarisation flags | Completed | UAT-1 | 2025-12-06 | 2025-12-10 | 2025-12-06 | 2025-12-10
47 | 6.3 | Manufacturing - Human Resource | 4 | Frontend Dev | 5 | Navneet | 3 wage formulas + GoM compliance warnings + 8 intervention types | Completed | UAT-1 | 2025-12-11 | 2025-12-14 | 2025-12-11 | 2025-12-14
48 | 6.4 | Pricing - Unit Pricing | 8 | Frontend Dev | 6.1,6.2,6.3 | Navneet | 9-section cost buildup + 3 pricing methods x 2 channels | Completed | UAT-1 | 2025-12-15 | 2025-12-22 | 2025-12-15 | 2025-12-22
49 | 6.5 | Market - Market Research | 158 | Frontend Dev | 5 | Navneet | 4 sections + competitive pricing + SWOT (auto-avg cross-feed pending) | In Progress | UAT-1 | 2025-12-23 | 2026-05-28 | 2025-12-23
50 | 6.6 | Market - Customer Analysis | 4 | Frontend Dev | 5 | Navneet | 6 segmentations + Existing/Required intervention toggles | Completed | UAT-1 | 2025-12-26 | 2025-12-29 | 2025-12-26 | 2025-12-29
51 | 6.7 | Market - Market Linkage | 4 | Frontend Dev | 5 | Navneet | Channel revenue tracking + annualized revenue calc | Completed | UAT-1 | 2025-12-30 | 2026-01-02 | 2025-12-30 | 2026-01-02
52 | 6.8 | Market - Promotions | 3 | Frontend Dev | 5 | Navneet | Existing + Required table with channel/mode/platform + frequency | Completed | UAT-1 | 2026-01-03 | 2026-01-05 | 2026-01-03 | 2026-01-05
53 | 6.9 | Product Dev - Registration & Licensing | 5 | Frontend Dev | 5 | Navneet | 20-type master + Lifetime Validity conditional + status chips + 5-status pipeline | Completed | UAT-1 | 2026-01-06 | 2026-01-10 | 2026-01-06 | 2026-01-10
54 | 6.10 | Product Dev - Prototyping | 4 | Frontend Dev | 5 | Navneet | Conditional dropdown (Packaging/Product) + iteration child table | Completed | UAT-1 | 2026-01-11 | 2026-01-14 | 2026-01-11 | 2026-01-14
55 | 6.11 | Product Dev - Testing | 4 | Frontend Dev | 5 | Navneet | 14 test types + 12 labs + consent management + date chain validation | Completed | UAT-1 | 2026-01-15 | 2026-01-18 | 2026-01-15 | 2026-01-18
56 | 6.12 | Product Dev - Standardization | 4 | Frontend Dev | 5 | Navneet | 13 SOP types + auto Product Sector + version tracking | Completed | UAT-1 | 2026-01-19 | 2026-01-22 | 2026-01-19 | 2026-01-22
57 | 6.13 | Product Dev - Quality Control | 6 | Frontend Dev | 5 | Navneet | 23-question star rating + average + maturity tier + distribution chart | Completed | UAT-1 | 2026-01-23 | 2026-01-28 | 2026-01-23 | 2026-01-28
58 | 6.14 | Product Dev - Packaging | 7 | Frontend Dev | 5 | Navneet | Per-variant detail + monthly qty matrix + sealing multi-select | Completed | UAT-1 | 2026-01-29 | 2026-02-04 | 2026-01-29 | 2026-02-04
59 | 6.15 | Marketing Tools - Brand Name | 4 | Frontend Dev | 5 | Navneet | Dual approval flow + market scope chips + log book | Completed | UAT-1 | 2026-02-05 | 2026-02-08 | 2026-02-05 | 2026-02-08
60 | 6.16 | Marketing Tools - Logo | 3 | Frontend Dev | 6.15 | Navneet | Designer assignment + 3 drafts + dual approval | Completed | UAT-1 | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-11
61 | 6.17 | Marketing Tools - Business Card | 3 | Frontend Dev | 6.15 | Navneet | Auto-populated content + QR uploads | Completed | UAT-1 | 2026-02-12 | 2026-02-14 | 2026-02-12 | 2026-02-14
62 | 6.18 | Marketing Tools - Label | 102 | Frontend Dev | 5 | Navneet | Per-variant table + AI Generate storyline (Apoorva dep) + 5-status pipeline | In Progress | UAT-1 | 2026-02-15 | 2026-05-28 | 2026-02-15
63 | 6.19 | Marketing Tools - Brochure | 5 | Frontend Dev | 5 | Navneet | Brochure setup + product listings + status + log book | Completed | UAT-1 | 2026-02-22 | 2026-02-26 | 2026-02-22 | 2026-02-26
64 | 6.20 | Skilling - Digital Literacy | 4 | Frontend Dev | 5 | Navneet | Access & Devices + 9-platform star rating + intervention flags | Completed | UAT-1 | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02
65 | 6.21 | Skilling - Capacity Building | 6 | Frontend Dev | 5 | Navneet | Scorecard Gap calc + Past Trainings (6-dim stars) + Required gap analysis | Completed | UAT-1 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-08
66 | 6.22 | Skilling - Business Plan Canvas | 3 | Frontend Dev | 5 | Navneet | 9 Canvas sections + SWOT (BPC HTML pending from client) | Completed | UAT-1 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11
67 | 6.23 | Logistics - Packing | 5 | Frontend Dev | 5 | Navneet | Per-product transit packaging + monthly volume + cost calc | Completed | UAT-1 | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-16
68 | 6.24 | Logistics - Service | 5 | Frontend Dev | 5 | Navneet | Connectivity + available services + route blocks with leg tables | Completed | UAT-1 | 2026-03-17 | 2026-03-21 | 2026-03-17 | 2026-03-21
69 | 6.25 | Infrastructure (BE + EE + CE combined) | 67 | Frontend Dev | 5 | Navneet | BE plinth rate + EE auto from machinery + CE solarisation + Financial Model (PRIME/Innovation) | In Progress | UAT-1 | 2026-03-22 | 2026-05-28 | 2026-03-22
70 | 6.26 | Funding - Pitch Deck | 3 | Frontend Dev | 5 | Navneet | Summary (X/11 progress) + Existing + Required (11 slides) + log book | Completed | UAT-1 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-25
71 | 6.27 | Funding - Schemes | 5 | Frontend Dev | 5 | Navneet | 17-scheme master + loan details + EMI calc + Required pipeline | Completed | UAT-1 | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-03-30
72 | 7 | Research Notes | 6 | Developer | 3 | Navneet | Fessociates can log free-form research notes; optional EP linking | In Progress | UAT-2 | 2026-03-18 | 2026-06-05 | 2026-03-18
73 | 7.1 | Research Notes doctype backend | 2 | Backend Dev | 3 | Navneet | Doctype with 11 fields deployed; permissions wired | Completed | UAT-2 | 2026-03-18 | 2026-03-19 | 2026-03-18 | 2026-03-19
74 | 7.2 | Vue: Research Notes form (11 fields) | 4 | Frontend Dev | 7.1 | Navneet | Standard Frappe form with 11 fields renders + saves | Completed | UAT-2 | 2026-03-20 | 2026-03-23 | 2026-03-20 | 2026-03-23
75 | 7.3 | EP Profile linking (optional) | 5 | Backend Dev | 7.1,4.1 | Navneet | Note can be tagged to an entrepreneur; surfaces on EP profile | Not Started | UAT-2 | 2026-06-02 | 2026-06-05
76 | 8 | Village Survey | 12 | Developer | 3 | Navneet | Village-level survey form complete; geo-pins ready for Landscape Map | In Progress | UAT-2 | 2026-03-24 | 2026-06-09 | 2026-03-24
77 | 8.1 | Village Survey doctype backend | 2 | Backend Dev | 3 | Navneet | village_visit doctype with 16 picker child doctypes deployed | Completed | UAT-2 | 2026-03-24 | 2026-03-25 | 2026-03-24 | 2026-03-25
78 | 8.2 | Vue: Survey form (17 fields + geolocation) | 5 | Frontend Dev | 8.1 | Navneet | Form renders + saves; geolocation captured | Completed | UAT-2 | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-03-30
79 | 8.3 | Master pickers: crops + forest resources + livelihoods (16 pickers) | 5 | Backend Dev | 8.1 | Navneet | All 16 picker doctypes loaded with seed data | Completed | UAT-2 | 2026-03-31 | 2026-04-04 | 2026-03-31 | 2026-04-04
80 | 8.4 | Geo-tag -> Landscape Map integration (village pins) | 6 | Backend Dev | 8.2,10.1 | Navneet | Village pins render on Landscape Map with popup | Not Started | UAT-2 | 2026-06-02 | 2026-06-09
81 | 9 | Fellow Activity Logger | 60 | Developer | 5,6 | Navneet | Fessociates log activities (Calendar/Board) with cascading filters; sync to EP + Log Book | In Progress | UAT-1 | 2026-04-05 | 2026-05-28 | 2026-04-05
82 | 9.1 | Replace Tasks workspace with Activity Logger pages | 4 | Frontend Dev | 5,6 | Navneet | task_manager + task_manager_app + task_manager_grid pages deployed | Completed | UAT-1 | 2026-04-05 | 2026-04-08 | 2026-04-05 | 2026-04-08
83 | 9.2 | Vue: Calendar view (default) | 7 | Frontend Dev | 9.1 | Navneet | TaskManagerApp.vue renders calendar with activities | Completed | UAT-1 | 2026-04-09 | 2026-04-15 | 2026-04-09 | 2026-04-15
84 | 9.3 | Vue: Board view + toggle | 4 | Frontend Dev | 9.1 | Navneet | TaskManagerGrid.vue renders board; toggle between board/calendar | Completed | UAT-1 | 2026-04-16 | 2026-04-19 | 2026-04-16 | 2026-04-19
85 | 9.4 | 6 cascading filters (District -> Block -> EP -> Module -> Framework -> Task) | 38 | Frontend Dev | 9.2 | Navneet | All 6 levels cascade and reset downstream selections | In Progress | UAT-1 | 2026-04-20 | 2026-05-28 | 2026-04-20
86 | 9.5 | Activity form: branching logic (3 paths: EP-Framework / EP-NonFramework / NonEntrepreneur) | 35 | Frontend Dev | 9.2 | Navneet | Activity form branches correctly based on entrepreneur + framework selection | In Progress | UAT-1 | 2026-04-24 | 2026-05-28 | 2026-04-24
87 | 9.6 | Sync: framework activities -> Log Book tabs | 5 | Backend Dev | 9.5 | Navneet | Activity completion writes to corresponding framework Log Book | Not Started | UAT-2 | 2026-06-02 | 2026-06-06
88 | 9.7 | Sync: all EP activities -> Intervention Logs (read-only) | 5 | Backend Dev | 9.5,4.8 | Navneet | EP Profile -> Intervention Logs reflects every Activity Logger entry | Not Started | UAT-2 | 2026-06-02 | 2026-06-06
89 | 9.8 | Framework completion tracking (Not Started -> Completed -> xN) | 7 | Backend Dev | 9.7 | Navneet | Each framework status auto-updates on EP dashboard per activity completion | Not Started | UAT-2 | 2026-06-03 | 2026-06-09
90 | 10 | Landscape Dashboard | 60 | Developer | 4,8 | Navneet | Entrepreneurial Landscape Map with 6 filters + clustering + popup + village pins | In Progress | UAT-2 | 2026-04-10 | 2026-06-09 | 2026-04-10
91 | 10.1 | Vue: Entrepreneurial Landscape Map (6 filters + clustering + popup) | 50 | Frontend Dev | 4,8 | Navneet | Map renders all EPs as pins; 6-filter narrowing live; cluster on zoom-out | In Progress | UAT-2 | 2026-04-10 | 2026-06-05 | 2026-04-10
92 | 10.2 | Village Survey geo-pin overlay on Landscape Map | 8 | Backend Dev | 8.4,10.1 | Navneet | Village pins shown alongside EP pins with distinct icon | Not Started | UAT-2 | 2026-06-02 | 2026-06-09
93 | 11 | Milestone & Activity Tracker | 12 | Developer / Tech Lead | 1 | Navneet | Progress Matrix workspace with Overview/Activities/Timeline/RACI tabs | Completed | UAT-2 | 2026-04-01 | 2026-04-12 | 2026-04-01 | 2026-04-12
94 | 11.1 | Vue: Milestone Tracker dashboard (4 tabs + lollipop + Gantt) | 8 | Frontend Dev | 1 | Navneet | MilestoneTrackerDashboard.vue + 8 sub-components live; lollipop + Gantt render | Completed | UAT-2 | 2026-04-01 | 2026-04-08 | 2026-04-01 | 2026-04-08
95 | 11.2 | Workspace + Web Page + CHB deployment (Progress Matrix) | 1 | Tech Lead | 11.1 | Bhushan | /prime-rural-milestone-tracker live; Progress Matrix workspace seeded | Completed | UAT-2 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09
96 | 11.3 | Milestone Master + Milestone Activity records populated (26 + 85) | 3 | PM | 11.2 | Samarth | 26 milestones + 85 activities loaded from RACI sheet | Completed | UAT-2 | 2026-04-10 | 2026-04-12 | 2026-04-10 | 2026-04-12
97 | 12 | Intervention Dashboard & KPI Form |  | Developer + PM + Client |  | Navneet | Requirement finalisation needed - KPI form spec pending from client (post 20-May meeting) | Pending Requirements | UAT-3
98 | 12.1 | KPI form spec gathering from client (Minha + Alem) |  | PM + Client |  | Samarth | KPI list + form fields + dashboard wireframe signed off by MBMA | Pending Requirements | UAT-3
99 | 12.2 | Intervention Dashboard rebuild (KPIs + Sankey + drill-down) |  | Frontend Dev | 12.1 | Navneet | Dashboard reflects signed-off KPIs with live data + drill-down | Pending Requirements | UAT-3
100 | 12.3 | Sankey Flow component (already built; needs KPI wiring) | 7 | Frontend Dev |  | Navneet | SankeyFlow.vue renders MET -> Incubated/Supported -> sectors | Completed | Pre-UAT | 2026-04-11 | 2026-04-17 | 2026-04-11 | 2026-04-17
101 | 13 | Apoorva AI Integration |  | Developer + Client |  | Navneet | Requirement finalisation needed - integration spec pending from Apoorva AI team | Pending Requirements | UAT-3
102 | 13.1 | Integration spec with Apoorva AI team (endpoints + auth + context model) |  | PM + Client |  | Samarth | API contract signed; auth + rate limits agreed | Pending Requirements | UAT-3
103 | 13.2 | Chatbot widget on portal (entrepreneur-facing) |  | Frontend Dev | 13.1 | Navneet | Widget docks on portal; sends + receives messages | Pending Requirements | UAT-3
104 | 13.3 | AI Generate: Label Storyline (in Labels Required tab) |  | Backend Dev | 13.1 | Navneet | Button on Label form generates storyline draft via Apoorva | Pending Requirements | UAT-3
105 | 13.4 | AI Generate: Brochure Storyline (in Brochure form) |  | Backend Dev | 13.1 | Navneet | Button on Brochure form generates storyline draft via Apoorva | Pending Requirements | UAT-3
106 | 13.5 | Context-aware responses (pass entrepreneur data to model) |  | Backend Dev | 13.1 | Navneet | Chatbot answers reference the current entrepreneur's data | Pending Requirements | UAT-3
107 | 14 | Claude-based Chatbot |  | Developer + Client |  | Navneet | Requirement finalisation needed - scope of Claude vs Apoorva to be agreed | Pending Requirements | UAT-3
108 | 14.1 | Claude integration spec (MCP scope, tool list, auth model) |  | PM + Client |  | Samarth | Tool list + auth model + which user roles get access agreed | Pending Requirements | UAT-3
109 | 14.2 | Internal-team chatbot widget (Core Team IT / PM use) |  | Frontend Dev | 14.1 | Navneet | Chatbot panel for internal users with MCP-powered queries | Pending Requirements | UAT-3
110 | 14.3 | Tool integration: entrepreneur queries, status updates, dashboard pulls |  | Backend Dev | 14.1 | Navneet | MCP server exposes write tools beyond current read-only set | Pending Requirements | UAT-3
111 | 15 | QA, VAPT & Performance | 40 | Testing / DevOps / Tech Lead | all | Chitranshi | All UAT cycles run; VAPT + load tests cleared before go-live | In Progress | UAT-1 | 2026-05-25 | 2026-07-03 | 2026-05-25
112 | 15.1 | UAT environment setup (separate from staging) | 3 | DevOps | 1 | Prakash | uat.prime-rural.dhwaniris.in live with prod-like data snapshot | In Progress | UAT-1 | 2026-05-25 | 2026-05-28 | 2026-05-25
113 | 15.2 | UAT-1 test scripts (User Mgmt + Masters + EP + Product + 27 frameworks + Activity Logger) | 3 | QA Engineer | 15.1 | Chitranshi | Test scripts cover BRD E2E for UAT-1 scope; checklist signed off | In Progress | UAT-1 | 2026-05-26 | 2026-05-28 | 2026-05-26
114 | 15.3 | UAT-1 internal dry run | 1 | QA + PM | 15.2 | Chitranshi / Samarth | Critical bugs from dry run fixed before client UAT | Not Started | UAT-1 | 2026-05-28 | 2026-05-28
115 | 15.4 | UAT-1 with client (MBMA team) | 1 | PM + Client | 15.3 | Samarth | Client signs off UAT-1 scope or files defects | Not Started | UAT-1 | 2026-05-29 | 2026-05-29
116 | 15.5 | UAT-1 bug fixing sprint | 5 | Tech Lead + Developer | 15.4 | Bhushan | All UAT-1 P0/P1 defects fixed + redeployed | Not Started | UAT-1 | 2026-05-30 | 2026-06-05
117 | 15.6 | UAT-2 test scripts (Research Notes + Village Survey + Landscape + Milestone Tracker) | 4 | QA Engineer | 15.5 | Chitranshi | Test scripts for UAT-2 scope signed off | Not Started | UAT-2 | 2026-06-08 | 2026-06-11
118 | 15.7 | UAT-2 with client (MBMA team) | 1 | PM + Client | 15.6 | Samarth | Client signs off UAT-2 scope | Not Started | UAT-2 | 2026-06-12 | 2026-06-12
119 | 15.8 | UAT-2 bug fixing sprint | 5 | Tech Lead + Developer | 15.7 | Bhushan | All UAT-2 P0/P1 defects fixed + redeployed | Not Started | UAT-2 | 2026-06-13 | 2026-06-19
120 | 15.9 | OWASP ZAP scan + role-based access + SQLi/XSS testing | 5 | Security Eng | 15.5 | Chitranshi | VAPT report - no Critical/High open findings | Not Started | Pre-Go-Live | 2026-06-22 | 2026-06-26
121 | 15.10 | Load test: 80 concurrent + 1200 EPs + 2000 map pins | 5 | QA Engineer | 15.5 | Chitranshi | Page load < 3s; API < 1s; map renders smoothly | Not Started | Pre-Go-Live | 2026-06-29 | 2026-07-03
122 | 16 | UAT & Go-Live | 25 | Developer / DevOps / PM / Client | 15 | Samarth | Production cutover with MBMA sign-off + 80 fellows onboarded | Not Started | Go-Live | 2026-07-06 | 2026-08-03
123 | 16.1 | UAT-3 scope finalization (post requirement gathering) |  | PM + Client | 12.1,13.1,14.1 | Samarth | UAT-3 scope: Intervention Dashboard + Apoorva AI + Claude Chatbot - dates set once specs sign off | Pending Requirements | UAT-3
124 | 16.2 | Production environment setup + SSL + domain | 5 | DevOps | 15 | Prakash | prime-rural.dhwaniris.in live with HTTPS + backups configured | Not Started | Go-Live | 2026-07-06 | 2026-07-10
125 | 16.3 | Data migration: Google Sheets -> Frappe | 5 | Backend Dev | 16.2 | Navneet | Legacy 32-framework data + entrepreneur records migrated + validated | Not Started | Go-Live | 2026-07-13 | 2026-07-17
126 | 16.4 | User onboarding: 80 fellows + coordinators | 5 | PM | 16.3 | Samarth | All users invited; passwords set; first login captured | Not Started | Go-Live | 2026-07-20 | 2026-07-24
127 | 16.5 | Training sessions for field users (Fessociates + Coordinators) | 5 | PM | 16.4 | Samarth | All 80 users trained; recordings shared; FAQ doc published | Not Started | Go-Live | 2026-07-27 | 2026-07-31
128 | 16.6 | Go-live sign-off from MBMA | 1 | PM + Client | 16.5 | Samarth | Signed handover note + MoM filed | Not Started | Go-Live | 2026-08-03 | 2026-08-03

## Gantt Chart
UAT Phase | Milestone (WBS L1) | Status | Planned Start | Planned End | Notes
Pre-UAT | 1. System Foundation | Completed | 2025-09-01 | 2025-09-14
UAT-1 | 2. User Management | In Progress | 2025-10-10 | 2026-05-28 | Target UAT-1: 29-May-2026
UAT-1 | 3. Masters | Completed | 2025-09-15 | 2025-10-05 | Target UAT-1: 29-May-2026
UAT-1 | 4. Entrepreneur Profile | In Progress | 2025-10-06 | 2026-05-28 | Target UAT-1: 29-May-2026
UAT-1 | 5. Product Profile | In Progress | 2025-11-06 | 2026-05-28 | Target UAT-1: 29-May-2026
UAT-1 | 6. Diagnostic Frameworks (27) | In Progress | 2025-12-01 | 2026-05-28 | Target UAT-1: 29-May-2026
UAT-2 | 7. Research Notes | In Progress | 2026-03-18 | 2026-06-05 | Target UAT-2: 12-Jun-2026 (proposed)
UAT-2 | 8. Village Survey | In Progress | 2026-03-24 | 2026-06-09 | Target UAT-2: 12-Jun-2026 (proposed)
UAT-1 | 9. Fellow Activity Logger | In Progress | 2026-04-05 | 2026-05-28 | Target UAT-1: 29-May-2026
UAT-2 | 10. Landscape Dashboard | In Progress | 2026-04-10 | 2026-06-09 | Target UAT-2: 12-Jun-2026 (proposed)
UAT-2 | 11. Milestone & Activity Tracker | Completed | 2026-04-01 | 2026-04-12 | Target UAT-2: 12-Jun-2026 (proposed)
UAT-3 | 12. Intervention Dashboard & KPI Form | Pending Requirements |  |  | Dates TBD - requirement finalisation needed
UAT-3 | 13. Apoorva AI Integration | Pending Requirements |  |  | Dates TBD - requirement finalisation needed
UAT-3 | 14. Claude-based Chatbot | Pending Requirements |  |  | Dates TBD - requirement finalisation needed
UAT-1 | 15. QA, VAPT & Performance | In Progress | 2026-05-25 | 2026-07-03 | Target UAT-1: 29-May-2026
Go-Live | 16. UAT & Go-Live | Not Started | 2026-07-06 | 2026-08-03

## How to use this document
Before you begin
1 | Read the Dhwani Setu methodology PM template guidance before editing this plan.
2 | Save a backup before bulk-editing rows. Update Plan Version + Plan Date on Header sheet on every change.
How to use this document
1 | Project Plan sheet is the master. WBS L1 rows are milestones (colored by status). L2 rows are sub-activities (white).
2 | UAT Batch column groups activities by delivery phase: UAT-1 (29-May-2026), UAT-2 (12-Jun-2026 proposed), UAT-3 (TBD post-requirements), Pre-UAT, Pre-Go-Live, Go-Live.
3 | AutoFilter is on - use the dropdown arrows on row 1 to filter by Status, Owner, UAT Batch, etc.
4 | Status values: Completed (green), In Progress (blue), Pending Requirements (orange), Not Started (grey). Pending Requirements means spec from client/SME is needed before dates can be set.
5 | Owners follow the project mapping: Navneet (developer), Bhushan (tech lead), Samarth (PM), Chitranshi/Samarth (testing), Prakash (DevOps), Client (MBMA / Apoorva / SMEs).
6 | Dates: Start/End = planned. Actual Start/End populated on completion. For Completed items, Planned and Actual match (backdated from real completion).
7 | Gantt Chart sheet is a milestone-level roll-up grouped by UAT Batch.
8 | Cells are never merged in the Project Plan data area, so filtering and sorting always work.
Change log
- | v6 rebuilt from v5 CSV and the actual repo state. Added UAT Batch column, owner reassignment, and backdated planned dates.

## Version Control
S No | Version | Date | Changes | Made By | Approved By | Current State
1 | v3 | 2026-03-23 | Initial client xlsx (329 rows). Columns: WBS, Activity, Duration, Resources, Dependency, Owner, Success Criteria, Current Status, Start/End/Actual dates. | Dhwani PM team | MBMA | Superseded
2 | v4 | 2026-05-10 | Mid-cycle refresh. Statuses adjusted manually. Not repo-validated. | Dhwani PM team | - | Superseded
3 | v5 | 2026-05-15 | CSV rebuild against repo (234 rows). Stripped date/duration/success criteria columns. Used to populate generated/data/project-plan.js -> plan.html. | Samarth (PM) + Claude | - | Superseded
4 | v6 | 2026-05-26 | Cut on Dhwani Setu PM template. 16 WBS roots: 14 user-named milestones + System Foundation + UAT/Go-Live. Owners reassigned (Navneet=Dev, Bhushan=TL, Samarth=PM, Chitranshi=Test, Prakash=DevOps, Client). UAT Batch column added. Planned dates backdated from actuals; tight clustering reflects AI-assisted build velocity. Intervention Dashboard, Apoorva AI, Claude Chatbot left at 'Pending Requirements' with no dates. | Samarth (PM) + Claude | Pending MBMA review | Published